## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. | [8 empty] | Period Highlight: | 11 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | Plan Date | PLAN START | End Date | PLAN DURATION | Actual Date | ACTUAL START | Actual End Date | ACTUAL DURATION | PERCENT COMPLETE | DAYS AFTER SEPTEMBER 7TH
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88
Submit project plan | 2017-09-18 | 11 | 2017-09-18 | 1 |  | 0 |  | 1 | 80%
Submit status report | 2017-09-20 | 13 | 2017-09-20 | 1 |  | 0 |  | 1 | 0%
Submit requirements specifications & analysis | 2017-10-02 | 25 | 2017-10-02 | 1 |  | 0 |  | 1 | 0%
Demonstrate prototype | 2017-10-11 | 34 | 2017-10-11 | 1 |  | 0 |  | 1 | 0%
Submit status report | 2017-10-16 | 39 | 2017-10-16 | 1 |  | 0 |  | 1 | 0%
Submit detailed design | 2017-10-25 | 48 | 2017-10-25 | 1 |  | 0 |  | 1 | 0%
Submit status report | 2017-11-01 | 55 | 2017-11-01 | 1 |  | 0 |  | 1 | 0%
Submit status report | 2017-11-15 | 69 | 2017-11-15 | 1 |  | 0 |  | 1 | 0%
Demonstrate project | 2017-11-27 | 81 | 2017-11-27 | 1 |  | 0 |  | 1 | 0%
Submit project code, user's guide, maintenance guide | 2017-12-04 | 88 | 2017-12-04 | 1 |  | 0 |  | 1 | 0%
Requirements specification | 2017-09-08 | 1 | 2017-09-15 | 8 | 2017-09-08 | 1 | 2017-09-08 | 1 | 80%
Requirements list | 2017-09-08 | 1 | 2017-09-15 | 8 | 2017-09-08 | 1 | 2017-09-15 | 8 | 100%
Design | 2017-09-18 | 11 | 2017-09-22 | 5 |  | 0 |  | 1 | 40%
UML class diagrams | 2017-09-18 | 11 | 2017-09-22 | 5 |  | 0 |  | 1 | 0%
UI implementation | 2017-09-23 | 16 | 2017-11-01 | 40 |  | 0 |  | 1 | 0%
Java Swing interface | 2017-09-23 | 16 | 2017-09-29 | 7 |  | 0 |  | 1 | 0%
Game display | 2017-09-23 | 16 | 2017-09-29 | 7 |  | 0 |  | 1 | 0%
Graphic placeholders | 2017-09-23 | 16 | 2017-09-29 | 7 |  | 0 |  | 1 | 0%
Actual graphics | 2017-09-30 | 23 | 2017-10-20 | 21 |  | 0 |  | 1 | 0%
Pac-Man eating animation | 2017-11-22 | 76 | 2017-11-23 | 2 |  | 0 |  | 1 | 0%
Ghost moving animation | 2017-11-22 | 76 | 2017-11-25 | 4 |  | 0 |  | 1 | 0%
Ghost consumed animation | 2017-11-22 | 76 | 2017-11-25 | 4 |  | 0 |  | 1 | 0%
Ghost warning blinking animation | 2017-11-22 | 76 | 2017-11-23 | 2 |  | 0 |  | 1 | 0%
Power pellet blinking animation | 2017-11-22 | 76 | 2017-11-22 | 1 |  | 0 |  | 1 | 0%
Rotate sprites based on direction of travel | 2017-10-21 | 44 | 2017-11-10 | 21 |  | 0 |  | 1 | 0%
GUI User-input |  | 0 |  | 1 |  | 0 |  | 1 | 0%
Keyboard interface | 2017-09-23 | 16 | 2017-09-29 | 7 |  | 0 |  | 1 | 0%
Game logic implementation | 2017-10-04 | 27 | 2017-10-20 | 17 |  | 0 |  | 1 | 0%
Tick | 2017-09-30 | 23 | 2017-10-03 | 4 |  | 0 |  | 1 | 0%
Maze creation | 2017-10-07 | 30 | 2017-10-13 | 7 |  | 0 |  | 1 | 0%
Placing walls | 2017-10-07 | 30 | 2017-10-13 | 7 |  | 0 |  | 1 | 0%
Placing pellets | 2017-10-02 | 25 | 2017-10-06 | 5 |  | 0 |  | 1 | 0%
Movement mechanics | 2017-09-30 | 23 | 2017-10-06 | 7 |  | 0 |  | 1 | 0%
Collision logic | 2017-10-07 | 30 | 2017-10-10 | 4 |  | 0 |  | 1 | 0%
Ghost decision logic | 2017-10-04 | 27 | 2017-11-10 | 38 |  | 0 |  | 1 | 0%
Power pellet functionality | 2017-11-11 | 65 | 2017-11-17 | 7 |  | 0 |  | 1 | 0%
Change ghost decision logic | 2017-11-11 | 65 | 2017-11-17 | 7 |  | 0 |  | 1 | 0%
Modify collision logic | 2017-11-11 | 65 | 2017-11-17 | 7 |  | 0 |  | 1 | 0%
Score counter | 2017-10-11 | 34 | 2017-10-13 | 3 |  | 0 |  | 1 | 0%
Testing | 2017-11-18 | 72 | 2017-11-22 | 5 |  | 0 |  | 1 | 0%
JUnit testing | 2017-11-18 | 72 | 2017-11-22 | 5 |  | 0 |  | 1 | 0%
Developer testing | 2017-11-18 | 72 | 2017-11-22 | 5 |  | 0 |  | 1 | 0%
Documentation | 2017-11-25 | 79 | 2017-12-02 | 8 |  | 0 |  | 1 | 0%
Introduction and design | 2017-11-25 | 79 | 2017-12-02 | 8 |  | 0 |  | 1 | 0%
Class documentation | 2017-11-25 | 79 | 2017-12-02 | 8 |  | 0 |  | 1 | 0%
Method documentation | 2017-11-25 | 79 | 2017-12-02 | 8 |  | 0 |  | 1 | 0%
Note on L2: Author: Automatically adjusts to the current day
Note on B32: Author: Depends on actual graphics
Note on B37: Author: Depends on tick
Note on B43: Author: Depends on keyboard interface
Note on B45: Author: Depends on tick
Note on B47: Author: Depends on ghost decision logic
Note on B51: Author: Depends on collision logic and placing pellets